## Data
Lista de Gr.02 / DM4iRetail Gr#2 / Risco
# | Nome | Descrição: | Type Measure | Measure | Probability | Consequence | Impact | Owner
R1 | Abandonment of key-people | Some essencial members of the project may leave | Transfer/Sharing | Contracts | LO | HI | Medium | Supplier PM
R2 | Badly formed Requirements | The requirement specification may have ambigous, misleading, low detail requirements | Avoid | Meetings with TeamLeaders and PMs from both companies until they reach agreement on the level of detail. | MED | VHI | High | Supplier PM
R3 | Budget exceed | The final cost of the project may surpass the accepted budget | Accept (w/ Provision) | Reserve 70.000€ for risk | MED | HI | Medium | Supplier PM
R4 | Change avoidance | The client may show reluctance to use the new technology | Mitigate | Make a workshop to motivate and explain the benefits of the new technologies we offer. | HI | LO | LOW | Team Leader IE
R5 | Client dissapointment | The client may not be happy and cancel the project | Accept | No refund policy | MED | VHI | High | Supplier PM
R6 | Integration fail | The integration of DM4iRetail with iRetailERP may fail | Avoid | Understand the limitation of the old and new systems and test throughout the development iterations | LO | VHI | High | Team Leader IE
R7 | K-users/technician indisponibility | Some K-user or technician may be unvailable to perfom training | Mitigate | Reach an agreement on the test date | MED | LO | LOW | Supplier PM
R8 | Low skill | Some members may not have the skill needed to this project | Avoid | During recruitment, assess and test members skills | LO | MED | LOW | Supplier PM
R9 | Schedule delay | The defined schedule may be delayed by some incidentals | Accept (w/ Provision) | Delay the dependent tasks or use the slack times. | HI | HI | High | Supplier PM
R10 | Security breaches | Some security breaches can happen, exposing personal data and information that may harm the company | Accept | It is no possible to guarantee the system is completely failproof | VLO | HI | LOW | Team Leader BE
R11 | Team members low perfomance | Some team members may not perfom like they were suppose too | Mitigate | Evaluate the possibility of the member working better in the future and either fire him or give him a break | LO | HI | Medium | Team Leader BE
R12 | Warranty delay | The external supplier may delay the delivery of the warranty | Accept (w/ Provision) | We will offer a period of privisionary warranty | MED | MED | Medium | Supplier PM
R13 | Work tools malfunctions | The Hardware or software tools to do the project is done may fail | Transfer/Sharing | Have insurance to cover the failures and get replacement tools immediately | LO | HI | Medium | Team Leader IE
R14 | Delay in equipment acquisition | Make a contract with the company that supplies equipment making them pay for everyday delay | Transfer/Sharing | Make a contract with the company that supplies equipment making them pay for everyday delay | HI | VHI | High | Supplier PM