## Data
Lista de Gr.02 / DM4iRetail Gr#2 / Risco
# | Nome | Descrição: | Type Measure | Measure | Probability | Consequence | Impact | Owner
R2 | Badly formed Requirements | The requirement specification may have ambigous, misleading, low detail requirements | Avoid | Meetings with TeamLeaders and PMs from both companies until they reach agreement on the level of detail. | MED | VHI | High | Supplier PM
R3 | Budget exceed | The final cost of the project may surpass the accepted budget | Accept (w/ Provision) | Reserve 70.000€ for risk | MED | HI | Medium | Supplier PM
R9 | Schedule delay | The defined schedule may be delayed by some incidentals | Accept (w/ Provision) | Delay the dependent tasks or use the slack times. | HI | HI | High | Supplier PM
R14 | Delay in equipment acquisition | The iRetail technical leader reported that there are delays in the equipment’s acquisition. | Transfer/Sharing | Make a contract with the company that supplies equipment making them pay for everyday delay | HI | VHI | High | Supplier PM
R15 | Finance TL and Pilot coord. not available | They are unavailable for critical meetings | Mitigate | Schedule the meetings having in account their vacations period | LO | VHI | High | Supplier PM