## Data
Lista de Agile Task
Nome | Descrição: | Pai | Ciclo de Vida | Owner
Sprint-1-US3-Implementation-Classification | Implementation of the classification tool of the DM module. | Sprint 1 | Not Started | Tiago Miguel Pedro do Nascimento
Sprint-1-US3-Implementation-Scan | Implementation of the scan tool of the DM module. | Sprint 1 | Not Started | Artur José Lourenço Fonseca
Sprint-1-US4-Implementation-Browse | Implementation of the folder and document browsing tools of the DM module. | Sprint 1 | Not Started | Artur José Lourenço Fonseca
Sprint-1-US5-Implementation-Search | Implementation of the document text searching tools of the DM module. | Sprint 1 | Not Started | BE Team Leader
Sprint-1-US2-Implementation-Configuration | Implementation of the configuration tool of the DM module. | Sprint 1 | Not Started | BE Team Leader
Sprint-1-US3-Implementation-Register | Implementation of the register tool of the DM module. | Sprint 1 | Not Started | Tiago Miguel Pedro do Nascimento
Sprint-1-US2-Implementation-Management | Implementation of the management tool of the DM module. | Sprint 1 | Not Started | Artur José Lourenço Fonseca
Sprint-1-US2-Tests | Unit and functionality testing for the configuration and management tools of the DM module. | Sprint 1 | Not Started | Tiago Miguel Pedro do Nascimento
Sprint-1-US3-Tests | Unit and functionality testing of the scanning, upload, registering and classification tools of the DM module. | Sprint 1 | Not Started | Tiago Miguel Pedro do Nascimento
Sprint-1-US4-Tests | Unit and functionality testing of the folder and document browsing tools of the DM module. | Sprint 1 | Not Started | Artur José Lourenço Fonseca
Sprint-1-US5-Tests | Unit and functionality testing of the document text searching tools of the DM module. | Sprint 1 | Not Started | BE Team Leader
Sprint-1-US3-Implementation-Upload | Implementation of the upload tool of the DM module. | Sprint 1 | Not Started | BE Team Leader