**Instituto Superior Técnico**

**DM4iRetail – 1ª Entrega – 2 de Outubro de 2015**

**Turno: 5ª 17h30**

**Group:**

Tiago Nascimento, nº70493

Artur Fonseca, nº 75456

Miguel Cruz, nº 76102

**Description of the project**

From the developer’s side, our corporation, this project is to develop a new information system for the company iRetail, available to every worker in it, made of the following modules:

* Document management and workflow;
* Invoices approval;
* Purchasing management

The project will also include the preparation of the current resource plan and workers, and testing the system:

* Integration with the existing resource planning;
* Training of K-users and IT engineers;
* A pilot test of the system.

For the client company, iRetail, the purpose is to overcome the limitations of paper documents and their flow and thus:

* Improve the quality of the information;
* Increase the satisfaction of the employees;
* Optimize the purchasing processes;
* Increase the level of suppliers’ satisfaction;
* Reduce the paper flows;
* And reduce the administrative costs.

**Success Factors**

* Goals shall be clearly defined to avoid wrong or unneeded operations;
* All the needed requirements should be clearly defined;
* Workers should be willing to use a much different system, from paper to a computer system;
* The documentation and manuals must be accurate and complete to be useful;
* The training should be sufficient to make users and technicians able to work;
* Roles and responsibilities must be clearly defined;
* There should be a common language between the developers;
* The pilot test should cover most or all the operations the system offers.
* The acceptance tests should be enough to find errors;
* The system should be designed to allow for all the required functionality.

**Success Criteria**

* Time
  + The project plan shall be approved until November 20th;
  + The Pilot must not last more than one month;
  + The system should be operational five months after the approval of the project plan, with less than two weeks tolerance;
  + The external supplier shall offer a minimum warranty period of three months;
* Cost
  + Do not exceed the € 400 000 budget for the whole project (excluding network structures and hardware) ;
  + The accepted budget variance shall be less than 6%;
* Quality
  + The number of non-conformities during acceptance tests should not be greater than 10%;
  + The time for correction of conformities should be less than 48 hours;
  + The evaluation of the training sessions shouldn't score lower than 3.75, from 0 to 5.

**Expected Benefits**

* Reduction by 50% of employees’ complaints, considering the expected overall employees satisfaction, ensuring the reimbursement of expenses no later than 5 working days after submission;
* Ensure supplier’s invoices get approved less than 10 working days after reception;
* Based on the previous benefit, allow iRetail to negotiate better discounts from suppliers;
* Allow classification and search of documents, based on content attributes;
* Reduce paper costs and physical space for archiving paper by 50%;
* Reduce administrative and post costs by 20%.

**Work Breakdown Structure**

**Work Package Description**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| Main Package | Subpackage Name | Description | Milestones | Deliverable |
| Project Management | Requirements | The requirements document | Complete the document | No delivery |
| Resources | The needed resources, such as the existent software | Acquire all the needed software |
| Planning | The plan of the project development | Approve the plan by 20th November |
| Team | Appointing the project manager and team | Appoint the full team |
| Warranty | The warranty offered by the supplier |  |
| Documentation | Functional Specification | The document with the functionalities developed | Complete the specification of all the functionalities | Documentation |
| Technical Documentation | The documentation of all the modules | Document the whole system |
| Manuals | The manuals for using the system | Complete the manuals |
| Training | K-Users | Training K-users in Lisbon and Oporto | Finish the training | No delivery |
| Technical Training | Training technical engineers in Lisbon | Finish the training |
| Training Evaluation | Evaluation of the training sessions | Finish the evaluation |
| Document Management | Document’s Dematerialisation | Transform paper into electronic documents | Complete the functionality | Document Management |
| Document Availability | Make documents available, classified according to criteria |
| Standardization | Standardising documents based on classifications and standards |
| Cataloging | Catalog and index documents based on classifications |
| Search Engine | Make a search engine |
| Integration with iRetail | Integrate with iRetail | Complete the integration |
| Invoices Approval Module | Receive Payments | Receive payment information | Complete the functionality | Invoices Approval Module |
| Authority Levels Verification | Verifying copies of invoices for approval |
| Integration with iRetail | Integrate with iRetail | Complete the integration |
| Purchase Module | Archive | Archiving purchase documents | Complete the functionality | Purchase Module |
| Document Availability | Making documents available based on iRetail rules |
| Authority Levels Verification | Verify authority levels to approve an order |
| Integration with iRetail | Integrate with iRetail | Complete the integration |
| Test and Evaluation | Technical | Acceptance tests | All the tests are accepted | No delivery |
| Security | Security features implemented to follow regulations | The required security is verified |
| Pilot Evaluation | Pilot test to evaluate the system operability | The behavior of the system is accepted |